Statement of Work 02

Implementation, data migration and hypercare — issued under the Master Services Agreement dated 12 January 2026

This Statement of Work is entered into on 5 October 2026 between Cloudberry Software Limited of 3 Grand Canal Quay, Dublin 2, Ireland (“Cloudberry”) and Brackenhill Retail Limited of 12 Cathedral Yard, Leeds LS1 5AP (“Brackenhill”) and is made under and in accordance with the Master Services Agreement between the same parties dated 12 January 2026 (the “MSA”).

Brackenhill wishes to procure the implementation, data migration and hypercare services described below. This Statement of Work is to be read with the MSA. Capitalised terms not defined here have the meanings given in the MSA.

| Field | Detail |
| --- | --- |
| Statement of Work reference | SOW 02 |
| Master agreement | MSA dated 12 January 2026 |
| Project | Retail Analytics Platform rollout — 47 stores and online trading |
| Commencement date | 5 October 2026 |
| Planned completion | 28 February 2027 |
| Charges | As set out in Part 4 of this Statement of Work |
| Brackenhill project sponsor | Chief Operating Officer |
| Cloudberry project sponsor | Director of Delivery, EMEA |

Scope of Services

Cloudberry shall perform the services described in Part 1 and shall deliver the Deliverables described in Part 3 (the “Deliverables”). The following are excluded from scope and will be treated as chargeable variations if required:

•  Network infrastructure and firewall changes at Brackenhill sites or in Brackenhill's data centre.

•  Hardware, including scanners, handhelds and any device used to capture store data.

•  Data cleansing or remediation of source data beyond the transformation rules agreed in Part 5.

•  Training delivery to Brackenhill store staff in the United Kingdom and Ireland.

•  Recruitment, payroll and onboarding of Brackenhill super-users.

Definitions

| Term | Meaning |
| --- | --- |
| Acceptance | Brackenhill's written confirmation that a Deliverable meets the Acceptance Criteria for that Deliverable |
| Production Service | The production environment of the Cloudberry Retail Analytics platform under the Master Services Agreement |
| Rollout plan | The store-by-store rollout sequence agreed by the parties before Go-Live |
| Users | The individuals authorised by Brackenhill to use the Production Service under the Master Services Agreement |
| Acceptance Criteria | The criteria set out against each Deliverable in Part 3 |
| Deliverable | An output of the services identified in Part 3, which may be a document, configuration, report, piece of software or other artefact |
| Go-Live | The date on which the Production Service is made available to Brackenhill Users in accordance with the rollout plan |
| Milestone | A stage of the Project identified in Part 4 |
| Milestone Date | “Milestone Date” means Cloudberry's reasonable estimate of the date on which the Milestone will be completed |
| Project | The implementation, data migration and hypercare services described in this Statement of Work |
| Re-performance | Performance of work previously rejected by Brackenhill under Part 3 |
| Super-User | A Brackenhill employee nominated under Part 7 to act as the first point of contact for the service in their region |

Deliverables and Acceptance

| Ref | Deliverable | Acceptance Criteria |
| --- | --- | --- |
| D1 | Discovery and solution design report | Report delivered covering the eight agreed business processes, signed off by the Brackenhill IT Director |
| D2 | Environment build and configuration baseline | Environment available in the Production Service region, with role-based access configured against the agreed role matrix and successfully demonstrated |
| D3 | Store data extract and load | All in-scope store data loaded and reconciled to source, with a reconciliation report showing a variance of no more than 0.5% |
| D4 | Online trading integration | Order and returns flows end-to-end in the test environment, evidenced by agreed test scripts executed and passed |
| D5 | Reporting pack — 9 standard reports | Each report produced from live data and matching the reporting specification in Annex A to no material variance |
| D6 | Store rollout — 47 sites | Each site live in accordance with the rollout plan, with a signed site acceptance record per site |
| D7 | Super-user training and handover | At least 90% of nominated Super-Users assessed as competent by Cloudberry following a delivered training session |

Cloudberry shall notify Brackenhill in writing on delivery of each Deliverable. Brackenhill shall have 20 working days from delivery to test a Deliverable against its Acceptance Criteria and either accept it or reject it in writing, identifying the specific failures against those criteria. If Brackenhill does not respond within that period the Deliverable is deemed accepted. Where a Deliverable is rejected, Cloudberry shall Re-perform the work within 15 working days and re-submit it, and the same testing period applies on re-submission.

Milestones, Fees and Payment

| Milestone | Deliverables covered | Milestone Date | Charge (GBP) |
| --- | --- | --- | --- |
| M1 — Design sign-off | D1 | 13 November 2026 | 12,000 |
| M2 — Environment ready | D2 | 18 December 2026 | 9,000 |
| M3 — Data loaded and reconciled | D3 | 22 January 2027 | 12,000 |
| M4 — Integration complete | D4 | 12 February 2027 | 7,000 |
| M5 — Reporting pack accepted | D5 | 19 February 2027 | 5,000 |
| M6 — Store rollout complete | D6 | 26 February 2027 | 3,000 |
| Total |  |  | 48,000 |

Cloudberry shall be entitled to raise an invoice in respect of a Milestone on the Milestone Date set out above. Each invoice shall be payable 30 days from its date and shall set out the Milestone, the Deliverables accepted or deemed accepted in respect of it, and the amount payable. Brackenhill is not required to withhold any amount in respect of Deliverables that have not yet been accepted.

Governance, Roles and Responsibilities

| Activity | Cloudberry | Brackenhill |
| --- | --- | --- |
| Solution design | Accountable | Consulted |
| Environment provisioning | Responsible | Accountable |
| Network and firewall changes | Informed | Responsible |
| Data source extraction | Consulted | Responsible |
| Data transformation and load | Accountable | Consulted |
| Data quality sign-off | Informed | Accountable |
| Test script definition | Responsible | Accountable |
| User acceptance testing | Informational | Accountable |
| Super-user training | Responsible | Accountable |
| Hypercare support | Accountable | Consulted |

The Parties shall operate a weekly project call between the project managers for the duration of the Project. Either Party may escalate a matter to the project sponsors in Part 1 within two working days of it arising, and the sponsors shall meet within five working days of the escalation.

Key Personnel

The individuals named in this Part 6 shall carry out the roles set out against them for the duration of the Project. Cloudberry may at any time substitute any other individual for any of the individuals named in this Part 6, provided that the substitute has at least equivalent skills, qualifications and experience and Cloudberry has notified Brackenhill in writing of the substitution. Cloudberry shall bear all costs of substitution, including any handover required for continuity.

| Role | Named individual | Commitment |
| --- | --- | --- |
| Engagement lead | Fionnuala Deveraux | 2 days per week |
| Solution architect | Rahul Menon | 3 days per week |
| Data migration lead | Cillian Ó Braonáin | Full time from M2 to M4 |
| Integration engineer | Siobhan Kelleher | Full time from M3 to M5 |
| Reporting lead | Ana-Maria Dinescu | 2 days per week |

Super-Users and Training

| Region | Number of Super-Users | Delivery mode |
| --- | --- | --- |
| North | 9 | Remote, four sessions |
| Midlands and South | 12 | Remote, six sessions |
| Scotland and North West | 7 | Remote, four sessions |
| Ireland | 5 | On site, two sessions |
| Online trading | 6 | Remote, three sessions |

Cloudberry shall provide training materials in electronic format and shall record attendance. Training materials remain Brackenhill's property on delivery.

Assumptions and Dependencies

| Ref | Assumption or dependency | Owner |
| --- | --- | --- |
| A1 | Brackenhill provides access to systems and data within 5 working days of request | Brackenhill |
| A2 | Brackenhill's subject matter experts are available for 4 hours per week | Brackenhill |
| A3 | Source data is delivered in the format agreed in the data specification signed with the Master Services Agreement | Brackenhill |
| A4 | Store network connectivity is available at each rollout site | Brackenhill |
| A5 | Cloudberry is given the change approval required to deploy to the Production Service | Brackenhill |

Where an assumption or dependency is not met, Cloudberry shall notify Brackenhill within 2 working days and the Parties shall agree a revised plan under Part 9. No Milestone Date is varied unless and until a revised plan is agreed in accordance with Part 9.

Variations

Any work required by Brackenhill that falls outside the scope described in Part 1, or any change to the scope, the Milestone Dates or the Charges, is a variation. Work in respect of a variation shall not commence until the variation has been recorded in a change note signed by the Brackenhill project sponsor and the Cloudberry delivery director, setting out the change, the effect on the Milestone Dates, and the additional charge.

| Role | Additional day rate (GBP) | Currency |
| --- | --- | --- |
| Delivery manager | 1,150 | GBP |
| Consultant | 950 | GBP |
| Engineer | 1,050 | GBP |

Rates in this Part 9 are fixed for the duration of the Project. Travel time is not chargeable. A variation recorded in accordance with this Part 9 is not a change to the Charges described in Part 4 and does not reduce the amounts payable under Part 4.

Intellectual Property in Project Deliverables

All intellectual property rights in the Deliverables vest in Cloudberry on creation. Brackenhill is granted a perpetual, non-exclusive, royalty-free licence to use the Deliverables for the purposes of its business for so long as it subscribes to the Production Service.

Cloudberry may reuse Brackenhill's materials, configurations, store layouts, business process descriptions and any Brackenhill data incorporated into a Deliverable for the benefit of Cloudberry's other customers and may include them in Cloudberry's product documentation, provided that Cloudberry does not disclose Brackenhill's name or any Brackenhill trade mark.

Data Protection and Security

Cloudberry shall process Brackenhill personal data only on Brackenhill's documented instructions and in accordance with the data protection provisions of the MSA. Cloudberry shall notify Brackenhill of any personal data breach within 48 hours of becoming aware and shall provide such information as Brackenhill reasonably requires to comply with its obligation to the Information Commissioner within 72 hours.

Cloudberry shall maintain its ISO/IEC 27001 certification and shall provide the MSA compliance information on request. Cloudberry personnel engaged on the Project shall be subject to confidentiality obligations no less protective than those in the MSA and shall not be changed without notification under Part 6.

Subcontracting

Cloudberry shall perform the services described in this Statement of Work using the personnel named in Part 6 and the subcontractors named in the Order Form under the Master Services Agreement, and no others, unless it has first obtained Brackenhill's prior written consent to the additional or replacement subcontractor. Cloudberry shall at all times remain fully liable for the acts and omissions of each subcontractor, shall impose on each subcontractor written obligations no less protective than those in the MSA, and shall procure that no subcontractor's terms apply to Brackenhill or take precedence over the MSA or this Statement of Work.

Liability Under this Statement of Work

The aggregate liability of Cloudberry in respect of this Statement of Work, howsoever arising, shall not exceed 20% of the Charges payable under Part 4. This Part 13 takes precedence over any limitation of liability in the MSA in respect of the subject matter of this Statement of Work.

Nothing in this Part 13 limits either Party's liability for death or personal injury caused by negligence, for fraud, or for any liability that cannot lawfully be limited.

Governing Law and Jurisdiction

This Statement of Work is governed by the laws of England and Wales and the Parties submit to the exclusive jurisdiction of the courts of England and Wales. The governing law and jurisdiction provisions of the MSA apply to this Statement of Work and no other provision of the MSA is excluded by this Statement of Work.

Reporting Pack Specification

| Report | Refresh | Delivery format | Audience |
| --- | --- | --- | --- |
| Trading dashboard — daily | Daily by 07:00 | Web and PDF | Store and district managers |
| Regional performance — weekly | Weekly by Monday 09:00 | Web and CSV | Regional managers |
| Stock cover analysis | Nightly | Web | Buying teams |
| Markdown exception report | Nightly | Web and email alert | Buying and supply chain |
| Promotion elasticity | Weekly | Web | Commercial team |
| Returns and losses analysis | Weekly | Web and PDF | Finance |
| Customer basket analysis | Weekly | Web | Commercial team |
| Basket price and mix | Monthly | PDF | Board and finance |
| Payback analysis | Monthly | PDF | Commercial finance |

Each report shall be produced from live Production Service data and shall match the calculation specified for it in Annex A in no material respect. Material means a difference of more than 2% on any reported measure.

SIGNED for and on behalf of the Parties on the date first written above.

|  | Cloudberry Software Limited | Brackenhill Retail Limited |
| --- | --- | --- |
| Signature |  |  |
| Name | Órlaith Ní Bhraonáin | Halima Sattar |
| Title | Chief Commercial Officer | Chief Operating Officer |
| Date |  |  |